## Agile User Story
AGILE USER STORY
USER STORY ID | PRIORITY | AS A <type of user> | I WANT TO <perform some task> | SO THAT I CAN <achieve some goal> | STORY POINTS | SPRINT #
SA1.1 | High | System Administrator | View system users | Visualize people in the system | 5 | 1 | This section is for the drop-down list
SA1.2 | High | System Administrator | Create and modify system users | Create and modify people in the system | 5 | 1 | High
SA1.3 | High | System Administrator | Delete system users | Delete people from the system | 3 | 1 | Medium
SA2 | Medium | System Administrator | Assign to maintainers specific competencies | Identify maintainers capable to perform a certain activity | 3 | 3 | Low
SA3 | Medium | System Administrator | Associate the procedure to the Maintainer according to Maintenance Activities | Comunicate Maintainer to perform the procedure | 5 | 3
SA4 | Low | System Administrator | Associate a Standard Maintenance Procedure to each Maintenance Procedure | Provide a standard reference for each procedure | 3
SA5.1 | Low | System Administrator | View Workspace notes | Visualize additional notes for an entity | 5
SA5.2 | Low | System Administrator | Create and Modify Workspace notes | Provide and edit additional notes for an entity | 5
SA5.3 | Low | System Administrator | Delete Workspace notes | Delete additional notes for an entity | 3
SA6 | Low | System Administrator | Record every user access | Track system usage | 1
RM1.1 | Medium | System Administrator (Repository Management) | View a list of competences related to a specific task | Visualize competences for a certain task | 3
RM1.2 | Medium | System Administrator (Repository Management) | Create and Modify a list of competences related to a specific task | Create and modify competences for a certain task | 3
RM1.3 | Medium | System Administrator (Repository Management) | Delete a list of competences related to a specific task | Delete competences for a certain task | 2
RM2.1 | Low | System Administrator (Repository Management) | View a factory sites and factory areas | Know which Factory sites and Factory areas are occupied by Maintenance work | 3
RM2.2 | Low | System Administrator (Repository Management) | Create and Modify a factory sites and factory areas | Tell maintainers where a maintenance activity has to be performed | 3
RM2.3 | Low | System Administrator (Repository Management) | Delete a factory sites and factory areas | Remove a Factory site that is not occupied by any Maintenance work anymore | 2
RM3.1 | Low | System Administrator (Repository Management) | View a list of materials needed by a certain Maintenance Activity | Know which materials will be used by mainteiners to perform that activity | 3
RM3.2 | Low | System Administrator (Repository Management) | Create and Modify a list of materials needed by a certain Maintenance Activity | Add and update the materials availability for the Maintainers | 3
RM3.3 | Low | System Administrator (Repository Management) | Delete a list of materials needed by a certain Maintenance Activity | Remove the materials unusable or unnecessary | 2
RM4.1 | Medium | System Administrator (Repository Management) | View a list of Maintenance procedures | Assign Maintenance Procedures to Maintainers | 3
RM4.2 | Medium | System Administrator (Repository Management) | Create and Modify a list of Maintenance procedures | Add and update the Maintenance procedures | 3
RM4.3 | Medium | System Administrator (Repository Management) | Delete a list of Maintenance procedures | Remove the Maintenance procedures | 2
RM5 | Medium | System Administrator (Repository Management) | Assign to Maintainers every possibile competency needed by Maintenance Activities | Match Maintainers based on their competences to a specific task | 5 | 3
RM6 .1 | Low | System Administrator (Repository Management) | View a list of Maintenance typologies | Visualize all the Mantenance typologies | 3
RM6 .2 | Low | System Administrator (Repository Management) | Create and Modify a list of Maintenance typologies | Create and Modify all the Mantenance typologies | 3
RM6.3 | Low | System Administrator (Repository Management) | Delete a list of Maintenance typologies | Delete all the Mantanance typologies | 2
P1.1 | High | Planner | View Maintenance Activities | Associate procedures to Maintainers according to those Maintenance Activities | 3 | 2
P1.2 | High | Planner | Create and edit Maintenance Activities | Associate procedures to Maintainers according to those Maintenance Activities | 3 | 2
P1.3 | High | Planner | Delete Maintenance Activities | Associate procedures to Maintainers according to those Maintenance Activities | 2 | 2
P2 | Medium | Planner | View the list of scheduled Maintenance Activities ordered by week | Manage future Maintenance Activities | 5 | 2
P3 | Medium | Planner | Visualize informations relative to a specific Maintenance Activity | Verify a certain Maintenance Activity | 5 | 2
P4 | Medium | Planner | Assign a specific Maintenance Activity to a suitable Maintainer | Tell a Maintainer to perform a certain Maintenance Activity | 5 | 2
P5 | Low | Planner | When a Maintenance Activity is assigned to a Maintainer, notify that Maintainer and send an e-mail to the Production manager | Get a Maintainer to quickly perform that Maintenance Activity and let the Production Manager to keep track of the process | 13
P6 | Medium | Planner | Visualize informations relative to a specific Emergency Work Order | Verify a certain Emergency Work Order | 5 | 3
P7 | Medium | Planner | Assign a specific Emergency Work Order to a suitable Maintainer | Tell a Maintainer to perform a certain Emergency Work Order | 5 | 3
P8 | Low | Planner | Interrupt an interruptable Maintenance Activity | Assign an Emergency Work Order to a Maintainer if he is already busy on an other activity | 1
P9.1 | Low | Planner | View materials needed by a certain Maintenance Activity | Know which materials will be used by mainteiners to perform that activity | 3
P9.2 | Low | Planner | Create and edit materials needed by a certain Maintenance Activity | Tell the maintainer which materials they are going to use in order to perform that activity | 3
P9.3 | Low | Planner | Delete materials needed by a certain Maintenance Activity | Remove materials from that activity, avoiding useless transport issues by maintainers | 2
P10 | Medium | Planner | See a list of assigned tickets (EWO) | Track assigned Emergency Work Orders | 3
141