## Agile Product Backlog
AGILE PRODUCT BACKLOG
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | STORY | PRIORITY | STATUS | ASSIGNED TO SPRINT
Sprint 1
1 | Setup Github Backend Repository | " " | Marco Della Rocca | No | High | Complete | Yes | This section is for the drop-down list
2 | Setup Automated Tests | " " | Marco Della Rocca | No | Low | Complete | Yes | Yes | High | Complete
3 | Database Conceptual Design Users | " " | Rosario Frontino | No | Medium | Complete | Yes | No | Medium | In Progress
4 | Database Data Dictionary Users | " " | Rosario Frontino | No | Medium | Complete | Yes |  | Low | Not Started
5 | Database Logical Design Users | " " | Marco Della Rocca | No | Medium | Complete | Yes
6 | Backend Create Implementation Users | " " | Rosario Frontino | Yes | High | Complete | Yes
7 | Backend Read Implementation Users | " " | Marco Della Rocca | Yes | High | Complete | Yes
8 | Backend Update Implementation Users | " " | Marco Della Rocca | Yes | High | Complete | Yes
9 | Backend Delete Implementation Users | " " | Rosario Frontino | Yes | High | Complete | Yes
10 | Backend List Implementation Users | " " | Rosario Frontino | Yes | High | Complete | Yes
11 | Setup Server Instance | " " | Marco Della Rocca | No | High | Complete | Yes
12 | Setup Server Authentication | " " | Marco Della Rocca | No | Medium | Complete | Yes
13 | Install Server Software | " " | Marco Della Rocca | No | Medium | Complete | Yes
14 | Create Database | " " | Marco Della Rocca | No | Medium | Complete | Yes
15 | Setup Deploy Script | " " | Marco Della Rocca | No | Low | Complete | Yes
16 | Setup Github Admin Repository | " " | Alessandra Boccuzzi | No | High | Complete | Yes
17 | Start PM2 On Server Startup | " " | Marco Della Rocca | No | Low | Complete | Yes
18 | Frontend User List | " " | Alessia Di Francesco | Yes | High | Complete | Yes
19 | Frontend User Show | " " | Alessia Di Francesco | Yes | Medium | Complete | Yes
20 | Frontend User Create | " " | Alessandra Boccuzzi | Yes | Low | Complete | Yes
21 | Frontend User Edit | " " | Alessandra Boccuzzi | Yes | High | Complete | Yes
22 | Frontend User Delete | " " | Alessia Di Francesco | Yes | High | Complete | Yes
Sprint 2
23 | Frontend Login Page | " " | Alessia Di Francesco | No | High | Complete | Yes
24 | Backend User Authentication | " " | Marco Della Rocca | No | Low | Complete | Yes
28 | Backend Login | " " | Marco Della Rocca | No | Medium | Complete | Yes
25 | Database Conceptual Design Maintenance Activity | " " | Rosario Frontino | No | High | Complete | Yes
26 | Database Data Dictionary Maintenance Activity | " " | Rosario Frontino | No | High | Complete | Yes
27 | Database Logical Design Maintenance Activity | " " | Rosario Frontino | No | High | Complete | Yes
29 | Backend Create Maintenance Activity | " " | Rosario Frontino | Yes | High | Complete | Yes
30 | Backend Read Maintenance Activity | " " | Rosario Frontino | Yes | High | Complete | Yes
31 | Backend Update Maintenance Activity | " " | Rosario Frontino | Yes | Medium | Complete | Yes
32 | Backend Delete Maintenance Activity | " " | Rosario Frontino | Yes | Low | Complete | Yes
33 | Backend List Maintenance Activity | " " | Rosario Frontino | Yes | High | Complete | Yes
34 | Frontend Maintanance Activity List | " " | Alessia Di Francesco | Yes | High | Complete | Yes
35 | Frontend Maintanance Activity Show | " " | Alessandra Boccuzzi | Yes | High | Complete | Yes
36 | Frontend Maintanance Activity Create | " " | Alessandra Boccuzzi | Yes | High | Complete | Yes
37 | Frontend Maintanance Activity Edit | " " | Alessandra Boccuzzi | Yes | Medium | Complete | Yes
38 | Frontend Maintanance Activity Delete | " " | Alessia Di Francesco | Yes | Low | Complete | Yes
39 | Setup Deploy Script (Planner) | " " | Marco Della Rocca | No | Low | Complete | Yes
40 | Setup Github Planner Repository | " " | Alessia Di Francesco | No | High | Complete | Yes
41 | Backend List Maintenance Activity By Week | " " | Marco Della Rocca | Yes | Medium | Complete | Yes
42 | Frontend List Maintenance Activity By Week | " " | Alessia Di Francesco | Yes | Medium | Complete | Yes
43 | Backend Maintenance Activities Show (verify) | " " | Marco Della Rocca | Yes | High | Complete | Yes
44 | Frontend Maintenance Activities Show (verify) | " " | Alessandra Boccuzzi | Yes | Medium | Complete | Yes
45 | Frontend Maintenance Activities Assignment (week) | " " | Alessandra Boccuzzi | Yes | Medium | Complete | Yes
46 | Frontend Maintenance Activities Assignment (day) | " " | Alessandra Boccuzzi | Yes | Medium | Complete | Yes
47 | Backend Maintenance Availabilities (week) | " " | Marco Della Rocca | Yes | Medium | Complete | Yes
48 | Backend Maintenance Availabilities (day) | " " | Marco Della Rocca | Yes | Medium | Complete | Yes